## Y23 Timeline - Rev 1
Operation | Total Task Duration (mins) | Total Elapsed Time (mins) | Operation Mode | Operation Mode Power (Watts)
Bootup + Wired Checkout | 110 | 110 | Idle | 45.87 | Idle | Teleoperation | Autonomous | Sleep
Deployment | 45 | 155 | Idle | 45.87 | 45.87 | 58.2 | 58.52 | 10
Exit | 13 | 168 | Idle | 45.87
| 7 | 175 | Autonomous | 58.52
| 184 | 359 | Idle | 45.87 | Length of Time Vector
| 1020 | 1379 | Comms Closed | 45.87 | 8618
Surface Ops Checkout | 6 | 1385 | Idle | 45.87
| 41 | 1426 | Autonomous | 58.52
| 72 | 1498 | Idle | 45.87
| 360 | 1858 | Comms Closed | 45.87
| 6 | 1864 | Idle | 45.87
| 95 | 1959 | Autonomous | 58.52
| 18 | 1977 | Idle | 45.87
| 840 | 2817 | Comms Closed | 45.87
| 6 | 2823 | Idle | 45.87
| 36 | 2859 | Autonomous | 58.52
| 77 | 2936 | Idle | 45.87
| 360 | 3296 | Comms Closed | 45.87
Trek 1 | 25 | 3321 | Idle | 45.87
| 69 | 3390 | Autonomous | 58.52
| 25 | 3415 | Idle | 45.87
| 840 | 4255 | Comms Closed | 45.87
Shadow Operations | 25 | 4280 | Idle | 45.87
| 119 | 4399 | Autonomous | 58.52
| 34 | 4433 | Idle | 45.87
| 1380 | 5813 | Sleep | 10
| 360 | 6173 | Comms Closed | 45.87
Trek 2 | 16 | 6189 | Idle | 45.87
| 22 | 6211 | Autonomous | 58.52
| 19 | 6230 | Idle | 45.87
| 60 | 6290 | Autonomous | 58.52
| 42 | 6332 | Idle | 45.87
| 11 | 6343 | Autonomous | 58.52
| 840 | 7183 | Comms Closed | 45.87
| 25 | 7208 | Idle | 45.87
| 58 | 7266 | Autonomous | 58.52
| 34 | 7300 | Idle | 45.87
| 360 | 7660 | Comms Closed | 45.87
| 25 | 7685 | Idle | 45.87
| 83 | 7768 | Autonomous | 58.52
| 10 | 7778 | Idle | 45.87
| 840 | 8618 | Comms Closed | 45.87
Trek 3 - Autonomous Leave and Return | 25 |  | Idle
Autonomous
Autonomous

## Y23 Timeline - Rev 2
Operating Mode Power | Total Task Duration (mins) | Total Elapsed Duration (mins) | Total Mission Time (mins)
45.87 | 26 | 26 | 21470
45.87 | 6 | 32
45.87 | 13 | 45
45.87 | 156 | 201
45.87 | 156 | 357
45.87 | 39 | 396
45.87 | 13 | 409
45.87 | 13 | 422
45.87 | 45 | 467
45.87 | 6 | 473
45.87 | 19 | 492
45.87 | 13 | 505
45.87 | 6 | 511
45.87 | 204 | 715
45.87 | 13 | 728
58.52 | 7 | 735
45.87 | 26 | 761
45.87 | 39 | 800
45.87 | 13 | 813
45.87 | 6 | 819
45.87 | 106 | 925
45.87 | 1022 | 1947
45.87 | 120 | 2067
45.87 | 6 | 2073
45.87 | 6 | 2079
58.52 | 41 | 2120
45.87 | 26 | 2146
45.87 | 6 | 2152
45.87 | 40 | 2192
45.87 | 360 | 2552
45.87 | 120 | 2672
45.87 | 6 | 2678
45.87 | 6 | 2684
58.52 | 39 | 2723
58.52 | 56 | 2779
45.87 | 6 | 2785
45.87 | 12 | 2797
45.87 | 840 | 3637
45.87 | 120 | 3757
45.87 | 6 | 3763
58.52 | 36 | 3799
45.87 | 6 | 3805
45.87 | 6 | 3811
45.87 | 71 | 3882
45.87 | 360 | 4242
45.87 | 120 | 4362
45.87 | 6 | 4368
45.87 | 6 | 4374
45.87 | 19 | 4393
58.52 | 69 | 4462
45.87 | 6 | 4468
45.87 | 19 | 4487
45.87 | 840 | 5327
45.87 | 180 | 5507
45.87 | 6 | 5513
45.87 | 6 | 5519
45.87 | 19 | 5538
58.52 | 39 | 5577
58.52 | 80 | 5657
45.87 | 6 | 5663
45.87 | 28 | 5691
7.37 | 1380 | 7071
45.87 | 360 | 7431
45.87 | 120 | 7551
45.87 | 6 | 7557
45.87 | 6 | 7563
58.52 | 22 | 7585
45.87 | 19 | 7604
58.52 | 30 | 7634
58.52 | 30 | 7664
45.87 | 6 | 7670
45.87 | 5 | 7675
45.87 | 840 | 8515
45.87 | 120 | 8635
45.87 | 6 | 8641
45.87 | 6 | 8647
45.87 | 19 | 8666
58.52 | 26 | 8692
58.52 | 32 | 8724
45.87 | 6 | 8730
45.87 | 29 | 8759
45.87 | 360 | 9119
45.87 | 120 | 9239
45.87 | 6 | 9245
45.87 | 6 | 9251
45.87 | 19 | 9270
58.52 | 26 | 9296
58.52 | 36 | 9332
58.52 | 21 | 9353
45.87 | 6 | 9359
45.87 | 4 | 9363
45.87 | 840 | 10203
45.87 | 140 | 10343
45.87 | 6 | 10349
45.87 | 39 | 10388
58.52 | 19 | 10407
58.52 | 114 | 10521
45.87 | 0 | 10521
45.87 | 360 | 10881
45.87 | 120 | 11001
45.87 | 6 | 11007
45.87 | 6 | 11013
58.52 | 45 | 11058
45.87 | 6 | 11064
45.87 | 62 | 11126
45.87 | 840 | 11966
45.87 | 120 | 12086
45.87 | 6 | 12092
45.87 | 6 | 12098
58.52 | 28 | 12126
45.87 | 6 | 12132
58.52 | 17 | 12149
45.87 | 6 | 12155
58.52 | 17 | 12172
45.87 | 6 | 12178
58.52 | 15 | 12193
45.87 | 6 | 12199
45.87 | 10 | 12209
45.87 | 360 | 12569
45.87 | 120 | 12689
45.87 | 6 | 12695
45.87 | 39 | 12734
45.87 | 19 | 12753
45.87 | 94 | 12847
58.52 | 1320 | 14167
45.87 | 120 | 14287
45.87 | 6 | 14293
45.87 | 39 | 14332
45.87 | 6 | 14338
45.87 | 107 | 14445
45.87 | 840 | 15285
45.87 | 120 | 15405
45.87 | 6 | 15411
45.87 | 39 | 15450
58.52 | 30 | 15480
45.87 | 6 | 15486
45.87 | 77 | 15563
45.87 | 360 | 15923
45.87 | 120 | 16043
45.87 | 6 | 16049
45.87 | 39 | 16088
58.52 | 30 | 16118
45.87 | 6 | 16124
45.87 | 77 | 16201
45.87 | 840 | 17041
45.87 | 120 | 17161
45.87 | 6 | 17167
45.87 | 39 | 17206
58.52 | 30 | 17236
45.87 | 6 | 17242
45.87 | 77 | 17319
45.87 | 360 | 17679
45.87 | 120 | 17799
45.87 | 6 | 17805
45.87 | 39 | 17844
58.52 | 30 | 17874
45.87 | 6 | 17880
45.87 | 77 | 17957
45.87 | 840 | 18797
45.87 | 120 | 18917
45.87 | 6 | 18923
45.87 | 39 | 18962
58.52 | 30 | 18992
45.87 | 6 | 18998
45.87 | 77 | 19075
45.87 | 360 | 19435
45.87 | 120 | 19555
45.87 | 6 | 19561
45.87 | 39 | 19600
58.52 | 30 | 19630
45.87 | 6 | 19636
45.87 | 77 | 19713
45.87 | 840 | 20553
45.87 | 120 | 20673
45.87 | 6 | 20679
45.87 | 39 | 20718
58.52 | 30 | 20748
45.87 | 6 | 20754
45.87 | 77 | 20831
45.87 | 360 | 21191
45.87 | 120 | 21311
45.87 | 6 | 21317
45.87 | 39 | 21356
58.52 | 30 | 21386
45.87 | 6 | 21392
45.87 | 77 | 21469