## Y23 Timeline - Rev 1
Operation | Total Task Duration (mins) | Total Elapsed Time (mins) | Operation Mode | Operation Mode Power (Watts)
Bootup + Wired Checkout | 110 | 110 | Idle | 45.87 | Idle | Teleoperation | Autonomous | Sleep
Deployment | 45 | 155 | Idle | 45.87 | 45.87 | 58.2 | 58.52 | 10
Exit | 13 | 168 | Idle | 45.87
| 7 | 175 | Autonomous | 58.52
| 184 | 359 | Idle | 45.87 | Length of Time Vector
| 1020 | 1379 | Comms Closed | 45.87 | 8618
Surface Ops Checkout | 6 | 1385 | Idle | 45.87
| 41 | 1426 | Autonomous | 58.52
| 72 | 1498 | Idle | 45.87
| 360 | 1858 | Comms Closed | 45.87
| 6 | 1864 | Idle | 45.87
| 95 | 1959 | Autonomous | 58.52
| 18 | 1977 | Idle | 45.87
| 840 | 2817 | Comms Closed | 45.87
| 6 | 2823 | Idle | 45.87
| 36 | 2859 | Autonomous | 58.52
| 77 | 2936 | Idle | 45.87
| 360 | 3296 | Comms Closed | 45.87
Trek 1 | 25 | 3321 | Idle | 45.87
| 69 | 3390 | Autonomous | 58.52
| 25 | 3415 | Idle | 45.87
| 840 | 4255 | Comms Closed | 45.87
Shadow Operations | 25 | 4280 | Idle | 45.87
| 119 | 4399 | Autonomous | 58.52
| 34 | 4433 | Idle | 45.87
| 1380 | 5813 | Sleep | 10
| 360 | 6173 | Comms Closed | 45.87
Trek 2 | 16 | 6189 | Idle | 45.87
| 22 | 6211 | Autonomous | 58.52
| 19 | 6230 | Idle | 45.87
| 60 | 6290 | Autonomous | 58.52
| 42 | 6332 | Idle | 45.87
| 11 | 6343 | Autonomous | 58.52
| 840 | 7183 | Comms Closed | 45.87
| 25 | 7208 | Idle | 45.87
| 58 | 7266 | Autonomous | 58.52
| 34 | 7300 | Idle | 45.87
| 360 | 7660 | Comms Closed | 45.87
| 25 | 7685 | Idle | 45.87
| 83 | 7768 | Autonomous | 58.52
| 10 | 7778 | Idle | 45.87
| 840 | 8618 | Comms Closed | 45.87
Trek 3 - Autonomous Leave and Return | 25 |  | Idle
Autonomous
Autonomous

## Y23 Timeline - Rev 2
Operation | Detailed Operation | MATLAB Array Index | Operating Mode Power | Total Task Duration (mins) | Total Elapsed Duration (mins) | Total Mission Time (mins)
05 Bootup + Wired Checkout
| Power On (Warm-up) | 1 | 45 | 26 | 26 | 21470
| Rover Status (Heartbeat) | 2 | 45 | 6 | 32
| Full System Check | 3 | 45 | 13 | 45
| Landing Coordinates Confirmed | 4 | 45 | 156 | 201
| Images of Environment | 5 | 45 | 156 | 357
| Wired Check (includes NSS checkout) | 6 | 45 | 39 | 396
| Wifi Communication Confirmed | 7 | 45 | 13 | 409
| Full System Check | 8 | 45 | 13 | 422
06 Deployment |  | 9 | 45 | 45 | 467
| Images of Surroundings | 10 | 45 | 6 | 473
| Plan Exit Route | 11 | 45 | 19 | 492
| Deployment Preperation | 12 | 45 | 13 | 505
| Deploy | 13 | 45 | 6 | 511
07 Exit |  | 14 | 45 | 204 | 715
| Full System Check | 15 | 45 | 13 | 728
| Rover Drives Away From Lander | 16 | 58 | 7 | 735
| Solar Panel | 17 | 45 | 26 | 761
| Cameras | 18 | 45 | 39 | 800
| Full System Check | 19 | 45 | 13 | 813
| Data downlink/analysis/delete | 20 | 45 | 6 | 819
| Communication window buffer | 21 | 45 | 106 | 925
COMM CLOSED |  | 22 | 45 | 1022 | 1947
08 Surface Operations Checkout |  | 23 | 45 | 120 | 2067
| Full System Check | 24 | 45 | 6 | 2073
| Data downlink/analysis/delete | 25 | 45 | 6 | 2079
| Teleoperation Checkout | 26 | 58 | 41 | 2120
| NSS Checkout | 27 | 45 | 26 | 2146
| Full System Check | 28 | 45 | 6 | 2152
| Communication window buffer | 29 | 45 | 40 | 2192
COMM CLOSED |  | 30 | 45 | 360 | 2552
|  | 31 | 45 | 120 | 2672
| Full System Check | 32 | 45 | 6 | 2678
| Data downlink/analysis/delete | 33 | 45 | 6 | 2684
| Autonomy Checkout | 34 | 58 | 39 | 2723
| Position Estimation Checkout | 35 | 58 | 56 | 2779
| Full System Check | 36 | 45 | 6 | 2785
| Communication window buffer | 37 | 45 | 12 | 2797
COMM CLOSED |  | 38 | 45 | 840 | 3637
|  | 39 | 45 | 120 | 3757
| Full System Check | 40 | 45 | 6 | 3763
| Science Checkout | 41 | 58 | 36 | 3799
| Data downlink/analysis/delete | 42 | 45 | 6 | 3805
| Full System Check | 43 | 45 | 6 | 3811
| Communication window buffer | 44 | 45 | 71 | 3882
COMM CLOSED |  | 45 | 45 | 360 | 4242
09 Trek 1 -- autonomous in comm, stable ice |  | 46 | 45 | 120 | 4362
| Full System Check | 47 | 45 | 6 | 4368
| Data downlink/analysis/delete | 48 | 45 | 6 | 4374
| Path Upload | 49 | 45 | 19 | 4393
| Drive Trek 1 | 50 | 58 | 69 | 4462
| Full System Check | 51 | 45 | 6 | 4468
| Communication window buffer | 52 | 45 | 19 | 4487
COMM CLOSED |  | 53 | 45 | 840 | 5327
10 SHADOW OPERATIONS |  | 54 | 45 | 180 | 5507
| Full System Check | 55 | 45 | 6 | 5513
| Data downlink/analysis/delete | 56 | 45 | 6 | 5519
| Path Upload | 57 | 45 | 19 | 5538
| Drive back to lander | 58 | 58 | 39 | 5577
| Teleop to safe position | 59 | 58 | 80 | 5657
| Full System Check | 60 | 45 | 6 | 5663
| Communication window buffer | 61 | 45 | 28 | 5691
10 Shadow Operations |  | 62 | 8 | 1380 | 7071
COMM CLOSED |  | 63 | 45 | 360 | 7431
11 Trek 2 -- PSR investigation |  | 64 | 45 | 120 | 7551
| Full System Check | 65 | 45 | 6 | 7557
| Data downlink/analysis/delete | 66 | 45 | 6 | 7563
| Teleop away from Lander | 67 | 58 | 22 | 7585
| PSR 1 -- path upload | 68 | 45 | 19 | 7604
| PSR 1 -- drive | 69 | 58 | 30 | 7634
| PSR 1 -- teleop science ops | 70 | 58 | 30 | 7664
| Full System Check | 71 | 45 | 6 | 7670
| Communication window buffer | 72 | 45 | 5 | 7675
COMM CLOSED |  | 73 | 45 | 840 | 8515
|  | 74 | 45 | 120 | 8635
| Full System Check | 75 | 45 | 6 | 8641
| Data downlink/analysis/delete | 76 | 45 | 6 | 8647
| PSR 2 -- path upload | 77 | 45 | 19 | 8666
| PSR 2 -- drive | 78 | 58 | 26 | 8692
| PSR 2 -- teleop science ops | 79 | 58 | 32 | 8724
| Full System Check | 80 | 45 | 6 | 8730
| Communication window buffer | 81 | 45 | 29 | 8759
COMM CLOSED |  | 82 | 45 | 360 | 9119
|  | 83 | 45 | 120 | 9239
| Full System Check | 84 | 45 | 6 | 9245
| Data downlink/analysis/delete | 85 | 45 | 6 | 9251
| PSR 3 -- path upload | 86 | 45 | 19 | 9270
| PSR 3 -- drive | 87 | 58 | 26 | 9296
| PSR 3 -- teleop science ops | 88 | 58 | 36 | 9332
| Preposition for Trek 3 | 89 | 58 | 21 | 9353
| Full System Check | 90 | 45 | 6 | 9359
| Communication window buffer | 91 | 45 | 4 | 9363
COMM CLOSED |  | 92 | 45 | 840 | 10203
12 Trek 3 -- autonomous leave and return |  | 93 | 45 | 140 | 10343
| Full System Check | 94 | 45 | 6 | 10349
| Data downlink/analysis/delete | 95 | 45 | 39 | 10388
| Upload Trek 3 | 96 | 58 | 19 | 10407
| Trek 3 autonomous leave/return | 97 | 58 | 114 | 10521
| Communication window buffer | 98 | 45 | 0 | 10521
COMM CLOSED |  | 99 | 45 | 360 | 10881
13 Collaborative Operations |  | 100 | 45 | 120 | 11001
| Full System Check | 101 | 45 | 6 | 11007
| Data downlink/analysis/delete | 102 | 45 | 6 | 11013
| Teleop for Payload Collab 1 (Heimdall) | 103 | 58 | 45 | 11058
| Full System Check | 104 | 45 | 6 | 11064
| Communication window buffer | 105 | 45 | 62 | 11126
COMM CLOSED |  | 106 | 45 | 840 | 11966
|  | 107 | 45 | 120 | 12086
| Full System Check | 108 | 45 | 6 | 12092
| Data downlink/analysis/delete | 109 | 45 | 6 | 12098
| Teleop Payload Collab 2 (Sampler) | 110 | 58 | 28 | 12126
| NSS Measurement | 111 | 45 | 6 | 12132
| Teleop Payload Collab 2 (MSolo) | 112 | 58 | 17 | 12149
| NSS Measurement | 113 | 45 | 6 | 12155
| Teleop Payload Collab 2 (MSolo) | 114 | 58 | 17 | 12172
| NSS Measurement | 115 | 45 | 6 | 12178
| Drive out of Collaborative zone | 116 | 58 | 15 | 12193
| Full System Check | 117 | 45 | 6 | 12199
| Communication window buffer | 118 | 45 | 10 | 12209
COMM CLOSED |  | 119 | 45 | 360 | 12569
14 Trek 4 -- long range autonomy, stable ice |  | 120 | 45 | 120 | 12689
| Full System Check | 121 | 45 | 6 | 12695
| Data downlink/analysis/delete | 122 | 45 | 39 | 12734
| Path upload | 123 | 45 | 19 | 12753
| Communication window buffer | 124 | 45 | 94 | 12847
COMM CLOSED | Drive Trek 4 | 125 | 58 | 1320 | 14167
|  | 126 | 45 | 120 | 14287
| Full System Check | 127 | 45 | 6 | 14293
| Data downlink/analysis/delete | 128 | 45 | 39 | 14332
| Full System Check | 129 | 45 | 6 | 14338
| Communication window buffer | 130 | 45 | 107 | 14445
COMM CLOSED |  | 131 | 45 | 840 | 15285
15 Extended Operations |  | 132 | 45 | 120 | 15405
| Full System Check | 133 | 45 | 6 | 15411
| Data downlink/analysis/delete | 134 | 45 | 39 | 15450
| Extended Operations 1 TBR | 135 | 58 | 30 | 15480
| Full System Check | 136 | 45 | 6 | 15486
| Communication window buffer | 137 | 45 | 77 | 15563
COMM CLOSED |  | 138 | 45 | 360 | 15923
|  | 139 | 45 | 120 | 16043
| Full System Check | 140 | 45 | 6 | 16049
| Data downlink/analysis/delete | 141 | 45 | 39 | 16088
| Extended Operations 2 TBR | 142 | 58 | 30 | 16118
| Full System Check | 143 | 45 | 6 | 16124
| Communication window buffer | 144 | 45 | 77 | 16201
COMM CLOSED |  | 145 | 45 | 840 | 17041
|  | 146 | 45 | 120 | 17161
| Full System Check | 147 | 45 | 6 | 17167
| Data downlink/analysis/delete | 148 | 45 | 39 | 17206
| Extended Operations 3 TBR | 149 | 58 | 30 | 17236
| Full System Check | 150 | 45 | 6 | 17242
| Communication window buffer | 151 | 45 | 77 | 17319
COMM CLOSED |  | 152 | 45 | 360 | 17679
|  | 153 | 45 | 120 | 17799
| Full System Check | 154 | 45 | 6 | 17805
| Data downlink/analysis/delete | 155 | 45 | 39 | 17844
| Extended Operations 4 TBR | 156 | 58 | 30 | 17874
| Full System Check | 157 | 45 | 6 | 17880
| Communication window buffer | 158 | 45 | 77 | 17957
COMM CLOSED |  | 159 | 45 | 840 | 18797
|  | 160 | 45 | 120 | 18917
| Full System Check | 161 | 45 | 6 | 18923
| Data downlink/analysis/delete | 162 | 45 | 39 | 18962
| Extended Operations 5 TBR | 163 | 58 | 30 | 18992
| Full System Check | 164 | 45 | 6 | 18998
| Communication window buffer | 165 | 45 | 77 | 19075
COMM CLOSED |  | 166 | 45 | 360 | 19435
|  | 167 | 45 | 120 | 19555
| Full System Check | 168 | 45 | 6 | 19561
| Data downlink/analysis/delete | 169 | 45 | 39 | 19600
| Extended Operations 6 TBR | 170 | 58 | 30 | 19630
| Full System Check | 171 | 45 | 6 | 19636
| Communication window buffer | 172 | 45 | 77 | 19713
COMM CLOSED |  | 173 | 45 | 840 | 20553
|  | 174 | 45 | 120 | 20673
| Full System Check | 175 | 45 | 6 | 20679
| Data downlink/analysis/delete | 176 | 45 | 39 | 20718
| Extended Operations 7 TBR | 177 | 58 | 30 | 20748
| Full System Check | 178 | 45 | 6 | 20754
| Communication window buffer | 179 | 45 | 77 | 20831
COMM CLOSED |  | 180 | 45 | 360 | 21191
16 Decommission Positioning |  | 181 | 45 | 120 | 21311
| Full System Check | 182 | 45 | 6 | 21317
| Data downlink/analysis/delete | 183 | 45 | 39 | 21356
| Decommision Operations TBR | 184 | 58 | 30 | 21386
| Full System Check | 185 | 45 | 6 | 21392
| Communication window buffer | 186 | 45 | 77 | 21469